## WIP Data
Extracted: 2026-08-28 13:23
Sewing Line Code | Sewing Line | Target Hours (OTP 100 Plan) | OTP Sewing Ratio | Target per Hour | Target for Day (with OT) | Target for Day (without OT) | Target Morning | Target Afternoon | Target OT | Actual Morning | Actual Morning (Extra) | Actual Afternoon | Actual Afternoon (Extra) | Actual OT | Morning Target Shortfall | WIP in Sewing Line | Sewn Yesterday | Bundled Waiting for Sewing (Full Day) | WIP Cut Waiting to be Bundled (4-12 hrs) | WIP Cut Waiting Health | Waiting to Cut | Lead Time Morning (hrs) | Lead Time Morning Health | Lead Time Morning Status | Lead Time Afternoon (hrs) | Lead Time Afternoon Health | Lead Time Afternoon Status | Lead Time OT (hrs) | Lead Time OT Status | Reason Missed Morning Target | Detail Morning | Afternoon Target Shortfall | Reason Missed Afternoon Target | Detail Afternoon | OT Target Shortfall (Full Day) | Reason Missed OT Target | Detail OT | Cause Category | Cut Waiting to be Bundled | Add: Cut Fully Bundled | Add: WIP Bundled Waiting for Sewing | OTP Sewing (Reference Date) | OT Total | Total without OT
VSEW001 | วารินทร์ / | 63 | 1.01 | 63.63 | 684.0225 | 493.1325 | 238.6125 | 254.52 | 190.89 | 30 | 180 | 180 | 96 |  | -208.6125 | 1134 | 473.4072 | 210 | 1.4144 | Underproduction |  | 13.6821 | Neutral | ปกติ | 14.2697 | Neutral | ปกติ | 10.2697 | ปกติ |  | 26-0388-2 T.12=180 | -283.1325 |  | 26-0388-2 T.13=96 26-0388-2 T.14=180 | -474.0225 | รอตัด | 26-0388-2 T.5=180 | กระจายไลน์ | 366 |  |  |  | 0.96 | 656.6616
VSEW003 | พิไลย์ / | 61 | 1 | 61 | 655.75 | 472.75 | 228.75 | 244 | 183 | 180 | 180 | 180 |  |  | -48.75 | 982 | 449.1125 | 360 | 3.2131 | Underproduction |  | 14.6375 | Neutral | ปกติ | 13.8383 | Neutral | ปกติ | 9.8383 | ปกติ |  | 26-0385-1 T.13=180 | -112.75 |  | 26-0385-1 T.14=180 | -295.75 | รอจัดงาน | 26-0385-1 T4=120 รอจัดงาน | รอปัก | 376 |  |  |  | 0.95 | 622.9625
VSEW004 | วงเดือน / | 54 | 0.93 | 50.22 | 539.865 | 389.205 | 188.325 | 200.88 | 150.66 | 120 | 240 | 120 | 80 |  | -68.325 | 466 | 342.5004 | 240 | 10.4938 | Neutral |  | 9.6276 | Neutral | ปกติ | 9.8601 | Neutral | ปกติ | 5.8601 | ต้องเร่งเติม |  | 25-0630-1 T.13=120 25-0630-1 T.14=120 25-0630-1 T.15=120 | -149.205 |  | 25-0630-1 T.16=120 25-0630-1 T.18=80 รอปักอกซ้าย นัดเบิก 15.00 | -299.865 | รอฟิวล์ | 25-0630-1 T.10=120 | รอฟิวล์ | 727 |  |  |  | 0.88 | 475.0812
VSEW005 | จินตนา / | 58 | 0.97 | 56.26 | 604.795 | 436.015 | 210.975 | 225.04 | 168.78 | 121 | 60 | 120 | 120 |  | -89.975 | 1118 | 401.1338 | 241 | 6.7366 | Neutral |  | 15.9592 | Neutral | ปกติ | 16.4751 | Neutral | ปกติ | 12.4751 | ปกติ |  | 25-0639-3 T.17=180 | -195.015 |  | 25-0639-3 T.18=180 | -363.795 | รอปัก | 25-0639-3 T.12=220 | รอพิมพ์ | 619 |  |  |  | 0.92 | 556.4114
VSEW007 | ส้ม / | 54 | 0.93 | 50.22 | 539.865 | 389.205 | 188.325 | 200.88 | 150.66 | 169 |  | 120 | 120 |  | -19.325 | 809 | 342.5004 | 289 | 5.3365 | Neutral |  | 12.6543 | Neutral | ปกติ | 13.6833 | Neutral | ปกติ | 9.6833 | ปกติ |  | 26-0472-1 จบ CW 20 = 169 | -100.205 |  | 26-0472-1 T.9=240 CW 19 | -250.865 |  |  | รอตัด | 508 |  |  |  | 0.88 | 475.0812
VSEW015 | ปัญญาพร / | 56 | 0.98 | 54.88 | 589.96 | 425.32 | 205.8 | 219.52 | 164.64 | 140 | 180 | 180 |  |  | -65.8 | 857 | 395.5476 | 320 | 0.49198 | Underproduction |  | 14.2393 | Neutral | ปกติ | 13.7692 | Neutral | ปกติ | 9.7692 | ปกติ |  | 26-0388-1 T.9=180 | -105.32 |  | 26-0388-1 T.7=180 | -269.96 | รอตัด | 26-0388-1 T.3=180 | บ่ายไม่เบิก | 207 |  |  |  | 0.93 | 548.6628
VSEW009 | สัมฤทธิ์ / | 66 | 0.95 | 62.7 | 674.025 | 485.925 | 235.125 | 250.8 | 188.1 | 270 |  | 123 | 200 |  | 34.875 | 956 | 437.3325 | 393 | 1.1164 | Underproduction |  | 12.5784 | Neutral | ปกติ | 13.9799 | Neutral | ปกติ | 9.9799 | ปกติ |  | 26-0392-1 T.5-7,3=270+80+22+21 | -92.925 |  | 26-0392-1 T.7,3=80+22+21/จบjob 26-0392-2 T.1=200 | -281.025 |  |  | รอตัดครบตัว | 393 |  |  |  | 0.9 | 606.6225
VSEW010 | นิชารัศ / | 63 | 1.03 | 64.89 | 697.5675 | 502.8975 | 243.3375 | 259.56 | 194.67 | 180 | 114 | 180 |  |  | -63.3375 | 1160 | 492.8395 | 360 | 1.7568 | Underproduction |  | 14.8122 | Neutral | ปกติ | 13.8361 | Neutral | ปกติ | 9.8361 | ปกติ |  | 26-0383-1 T.5=180 26-0383-1 T.6=114 | -142.8975 |  | 26-0383-1 T.7=180 | -337.5675 |  |  | รอเรียงวีราเน่ | 294 |  |  |  | 0.98 | 683.6161
VSEW012 | ราตรี / | 43 | 1.05 | 45.15 | 485.3625 | 349.9125 | 169.3125 | 180.6 | 135.45 | 216 |  | 120 | 120 |  | 46.6875 | 638 | 349.9125 | 336 | 3.278 | Underproduction |  | 11.1647 | Neutral | ปกติ | 12.7303 | Neutral | ปกติ | 8.7303 | ต้องเร่งเติม |  | 25-0621-3 T.3,4=96+120 | -13.9125 | รอปัก | 25-0621-3 T.4=240 | -149.3625 |  |  | รอจัดงานส่งงานเรียง | 388 |  |  |  | 1 | 485.3625
VSEW013 | สายรุ้ง / | 59 | 1.05 | 61.95 | 665.9625 | 480.1125 | 232.3125 | 247.8 | 185.85 | 220 |  | 200 | 120 |  | -12.3125 | 863 | 480.1125 | 420 | 12.5908 | Overproduction |  | 9.7318 | Neutral | ปกติ | 11.1473 | Neutral | ปกติ | 7.1473 | ต้องเร่งเติม |  | 25-0655-5T.1=200 | -60.1125 | รอปัก | 25-0655-5T.2=220 25-0655-5T.3=220 รอปักอกซ้าย | -245.9625 |  |  | จัดงานส่งปักช้า | 1100 |  |  |  | 1 | 665.9625
VSEW014 | รำไพ / | 54 | 0.95 | 51.3 | 551.475 | 397.575 | 192.375 | 205.2 | 153.9 | 160 |  | 148 | 134 |  | -32.375 | 635 | 198.7875 | 308 | 3.3528 | Underproduction |  | 11.6221 | Neutral | ปกติ | 13.3692 | Neutral | ปกติ | 9.3692 | ต้องเร่งเติม |  | 26-0335-1 T.11,12=80+80 | -89.575 |  | 26-0335-1 T.13=68 พร้อมส่ง 26-0335-1 T.14=80 พร้อมส่ง 26-0335-1 T.14,15,16=80+14+40 | -243.475 |  |  | รอ Pad Print | 454 |  |  |  | 0.5 | 275.7375
VSEW016 | อรอนงค์ / | 45 | 0.88 | 39.6 | 425.7 | 306.9 | 148.5 | 158.4 | 118.8 | 160 | 160 | 80 | 80 |  | 11.5 | 293 | 191.565 | 240 | 1.0606 | Underproduction |  | 10.6423 | Neutral | ปกติ | 10.9327 | Neutral | ปกติ | 6.9327 | ต้องเร่งเติม |  | 26-0302-2 T.,2.4=80*2 26-0302-2 T.5,6=80*2 | -66.9 |  | 26-0302-2 T.5,6=80+80 ขอซับใน 201 T5,6 | -185.7 |  |  | รอตัดฟองน้ำ | 202 |  |  |  | 0.45 | 191.565
VSEW017 | สำราญ / 70 | 70 | 1.05 | 73.5 | 790.125 | 569.625 | 275.625 | 294 | 220.5 | 280 |  | 280 | 156 |  | 4.375 | 1065 | 569.625 | 560 | 3.2653 | Underproduction |  | 10.5493 | Neutral | ปกติ | 12.7313 | Neutral | ปกติ | 8.7313 | ต้องเร่งเติม |  | 26-0683-2 T.10=280 | -9.625 |  | 26-0683-2 T.11.12.13=280+140+16 | -230.125 |  |  | รอตัดเก็บเศษ | 676 |  |  |  | 1 | 790.125
VS02+06 | นิภาพร + ชุติมันต์ | 40 | 0.88 | 35.2 | 378.4 | 272.8 | 132 | 140.8 | 105.6 | 200 | 93 | 16 | 60 |  | 68 | 460 | 122.76 | 216 | 6.4489 | Neutral |  | 17.9045 | Neutral | ปกติ | 16.3136 | Neutral | ปกติ | 12.3136 | ต้องเร่งเติม |  | 25-0760-2 T.2,3,4=200+93 | -56.8 |  | 25-0760-3 T.1= 60 | -162.4 |  |  | รอจัดงาน | 95 | 208 |  |  | 0.45 | 193.5
VS08+11 | นวลจันทร์+สุพิศ/ | 51 | 0.94 | 47.94 | 515.355 | 371.535 | 179.775 | 191.76 | 143.82 | 200 |  | 200 | 200 |  | 20.225 | 1050 | 487.9425 | 400 | -4.1719 | Underproduction |  | 15.8961 | Neutral | ปกติ | 20.4898 | Neutral | ปกติ | 16.4898 | ปกติ |  | 25-0651-3 T.9=200 | 28.465 | รอตัดฟองน้ำ | 25-0651-3 T.10=200 25-0651-3 T.12=200 | -115.355 |  |  | รอตรวจ | 200 |  |  |  | 0.89 | 487.9425