## WIP Data
Extracted: 2026-08-26 15:31
Sewing Line Code | Sewing Line | Target Hours (OTP 100 Plan) | OTP Sewing Ratio | Target per Hour | Target for Day (with OT) | Target for Day (without OT) | Target Morning | Target Afternoon | Target OT | Actual Morning | Actual Morning (Extra) | Actual Afternoon | Actual Afternoon (Extra) | Actual OT | Morning Target Shortfall | WIP in Sewing Line | Sewn Yesterday | Bundled Waiting for Sewing (Full Day) | WIP Cut Waiting to be Bundled (4-12 hrs) | WIP Cut Waiting Health | Waiting to Cut | Lead Time Morning (hrs) | Lead Time Morning Health | Lead Time Morning Status | Lead Time Afternoon (hrs) | Lead Time Afternoon Health | Lead Time Afternoon Status | Lead Time OT (hrs) | Lead Time OT Status | Reason Missed Morning Target | Detail Morning | Afternoon Target Shortfall | Reason Missed Afternoon Target | Detail Afternoon | OT Target Shortfall (Full Day) | Reason Missed OT Target | Detail OT | Cause Category | Cut Waiting to be Bundled | Add: Cut Fully Bundled | Add: WIP Bundled Waiting for Sewing | OTP Sewing (Reference Date) | OT Total | Total without OT
VSEW001 | วารินทร์ / | 61 | 1 | 61 | 655.75 | 472.75 | 228.75 | 244 | 183 | 180 |  | 180 |  | 180 | -48.75 | 1214 | 436 | 540 | -1.2787 | Underproduction |  | 15.7049 | Neutral | ปกติ | 14.9057 | Neutral | ปกติ | 13.8566 | ปกติ |  | 26-0331-3 T.9=180 | -112.75 |  | 26-0331-3 T.10=180 | -115.75 |  | 26-0331-3 T.11=180 | กระจายไลน์ | 282 |  |  | 0.75 | 491.8125 | 354.5625
VSEW003 | พิไลย์ / | 61 | 0.95 | 57.95 | 622.9625 | 449.1125 | 217.3125 | 231.8 | 173.85 | 90 | 180 | 180 |  |  | -127.3125 | 1225 | 591 | 270 | 0 | Underproduction |  | 15.5997 | Neutral | ปกติ | 14.9558 | Neutral | ปกติ | 10.9558 | ปกติ |  | 26-0323-3 T.8=60 จบ รอตัด 26-0328-1 T.8=180 พร้อมเบิก | -179.1125 |  | 26-0328-1 T.9=180 | -352.9625 | รอตัด | 26-0328-1 T.7,10,11=36+120+29 จบ รอตัด | รอปัก | 360 |  |  | 0.9 | 560.6662 | 404.2013
VSEW004 | วงเดือน / | 53 | 0.9 | 47.7 | 512.775 | 369.675 | 178.875 | 190.8 | 143.1 | 120 | 148 | 120 |  | 180 | -58.875 | 479 | 222 | 420 | 7.2537 | Neutral |  | 11.0063 | Neutral | ปกติ | 9.772 | Neutral | ปกติ | 9.5456 | ปกติ |  | 25-0697-1 T,3=28 นัดเบิก 10:30 | -129.675 |  | 25-0697-1 T,4=120 | -92.775 |  | 25-0697-1 T,5=120 | รอฟิวล์ | 794 |  |  | 0.88 | 451.242 | 325.314
VSEW005 | จินตนา / | 58 | 1 | 58 | 623.5 | 449.5 | 217.5 | 232 | 174 | 40 | 160 | 26 |  | 160 | -177.5 | 1340 | 592.325 | 226 | -2.069 | Underproduction |  | 17.2013 | Overproduction | ไม่ต้องทำเพิ่ม | 13.8996 | Neutral | ปกติ | 12.6582 | ปกติ |  | 25-0639-2 T.8=160 รอเรียงวีราเน่ปกนอกจัดงานเรียงวีราเน่ให้ | -383.5 |  | 25-0639-2 T.9,10=12+14 จบ | -397.5 | รอตัดครบตัว | 25-0639-3 รอตัดครบตัว ขอเบิกงาน 18:30 ได้งานครบตัวตอน 19.00 น. | รอพิมพ์ | 226 |  | 50 | 0.95 | 592.325 | 427.025
VSEW007 | ส้ม / | 54 | 0.88 | 47.52 | 510.84 | 368.28 | 178.2 | 190.08 | 142.56 | 139 |  | 113 | 37 | 28 | -39.2 | 657 | 179 | 280 | 0.79966 | Underproduction |  | 12.984 | Neutral | ปกติ | 12.3906 | Neutral | ปกติ | 10.2424 | ปกติ |  | 26-0397-2 T.2,3=84+55 | -116.28 |  | 26-0397-2 T.4,5=48+135 | -230.84 | รอฟิวล์ |  | รอตัด | 276 |  |  | 0.5 | 255.42 | 184.14
VSEW015 | ปัญญาพร / | 51 | 1.03 | 52.53 | 564.6975 | 407.1075 | 196.9875 | 210.12 | 157.59 | 60 | 180 |  | 110 | 120 | -136.9875 | 1064 | 525.1687 | 180 | -8.9473 | Underproduction | ตัดเสร็จ 09.00 | 14.8264 | Neutral | ปกติ | 13.1705 | Neutral | ปกติ | 12.5971 | ปกติ |  | 26-0330-1 T.6=180 / ขอใน1 T.4,5 | -347.1075 | รอตัด | 26-0330-1 T.7=110 นัดเบิก 16:00 | -384.6975 | รอจัดงาน | 26-0330-1 T.9=180 นัดเบิก 18:30 | บ่ายไม่เบิก |  |  |  | 0.93 | 525.1687 | 378.61
VSEW009 | สัมฤทธิ์ / | 66 | 0.95 | 62.7 | 674.025 | 485.925 | 235.125 | 250.8 | 188.1 | 180 |  | 180 |  | 180 | -55.125 | 1175 | 620.103 | 540 | -2.8708 | Underproduction |  | 11.7208 | Neutral | ปกติ | 10.8417 | Neutral | ปกติ | 9.7125 | ปกติ |  | 26-0329-2 T.4=180 | -125.925 |  | 26-0329-2 T.5=180 | -134.025 |  | 26-0329-2 T.6=180 | รอตัดครบตัว | 180 |  |  | 0.92 | 620.103 | 447.051
VSEW010 | นิชารัศ / | 63 | 1 | 63 | 677.25 | 488.25 | 236.25 | 252 | 189 | 270 | 180 | 60 | 120 | 180 | 33.75 | 952 | 643.3875 | 510 | -5.7143 | Underproduction |  | 12.0415 | Neutral | ปกติ | 11.1486 | Neutral | ปกติ | 10.0058 | ปกติ |  | 26-0313-4 T.1,2=90+180 26-0313-4 T.5=180 | -158.25 |  | 26-0314-4 T.3=60+120 | -167.25 |  | 26-0314-4 T.7=180 | รอเรียงวีราเน่ | 180 |  |  | 0.95 | 643.3875 | 463.8375
VSEW012 | ราตรี / | 44 | 1.05 | 46.2 | 496.65 | 358.05 | 173.25 | 184.8 | 138.6 | 180 | 60 | 60 | 55 | 165 | 6.75 | 755 | 456 | 405 | -3.4632 | Underproduction |  | 11.6667 | Neutral | ปกติ | 10.4058 | Neutral | ปกติ | 9.9773 | ปกติ |  | 25-0621-1=8=180+60 | -118.05 |  | 25-0621-1T.8,=60 25-0621-1T.9=55 | -91.65 |  | 25-0621-1T.9=165 | รอจัดงานส่งงานเรียง | 180 |  |  | 1 | 496.65 | 358.05
VSEW013 | สายรุ้ง / | 58 | 0.97 | 56.26 | 604.795 | 436.015 | 210.975 | 225.04 | 168.78 | 280 |  | 180 |  |  | 69.025 | 1078 | 556.4114 | 460 | 12.4422 | Neutral |  | 14.2479 | Neutral | ปกติ | 13.6974 | Neutral | ปกติ | 9.6974 | ปกติ |  | 25-0655-2 T.10,11=80+200 | 23.985 |  | 25-0655-2 T.12=180 | -144.795 |  |  | จัดงานส่งปักช้า | 880 |  |  | 0.92 | 556.4114 | 401.1338
VSEW014 | รำไพ / | 54 | 0.8 | 43.2 | 464.4 | 334.8 | 162 | 172.8 | 129.6 | 180 |  | 180 |  | 180 | 18 | 771 | 314 | 540 | -8.3333 | Underproduction | ํt.1 ตัดเสร็จ 08.45 | 14.7454 | Neutral | ปกติ | 15.162 | Neutral | ปกติ | 15.3287 | ปกติ |  | 26-0320-1 T.1=180 | 25.2 |  | 26-0320-1 T.2=180 | 75.6 |  |  | รอ Pad Print |  |  |  | 0.75 | 348.3 | 251.1
VSEW016 | อรอนงค์ / 71 | 71 | 0.92 | 65.32 | 702.19 | 506.23 | 244.95 | 261.28 | 195.96 | 100 | 200 | 200 |  | 100 | -144.95 | 662 | 421 | 400 | -3.0618 | Underproduction |  | 8.2823 | Underproduction | ต้องเร่งเติม | 7.5942 | Underproduction | ต้องเร่งเติม | 5.1251 | ต้องเร่งเติม |  | 26-0297-1 T,7=100 26-0297-1 T.8,10,=100 *2 | -206.23 |  | 26-0297-1 T,12=100 26-0297-1 T.13=100 | -302.19 |  | 26-0297-1 T,14=100 26-0297-1T.16,17=100*2 รอตัด | รอตัดฟองน้ำ | 100 | 200 |  | 0.5 | 351.095 | 253.115
VSEW017 | สำราญ / | 27 | 0.88 | 23.76 | 255.42 | 184.14 | 89.1 | 95.04 | 71.28 | 150 | 78 |  |  |  | 60.9 | 77 | 0 | 150 | 8.5017 | Neutral |  | 17.8872 | Overproduction | ไม่ต้องทำเพิ่ม | 14.1372 | Neutral | ปกติ | 10.1372 | ปกติ |  | 26-0355-1 T.3=150 | -34.14 |  | 26-0355-1 T.4,5=68+10 | -105.42 |  |  | รอตัดเก็บเศษ | 840 | -560 | 120 | 1 | 255.42 | 184.14
VSEW018 | VSEW018 ผ้าพันคอ | 58 | 0.96 | 55.68 | 598.56 | 431.52 | 208.8 | 222.72 | 167.04 | 300 |  | 300 |  |  | 91.2 | 1273 | 589 | 600 | 1.796 | Underproduction |  | 17.6724 | Overproduction | ไม่ต้องทำเพิ่ม | 19.3103 | Overproduction | ไม่ต้องทำเพิ่ม | 15.3103 | ปกติ |  | 26-0684-2 T.16=300 | 168.48 |  | 26-0684-2 T.19=300 | 1.44 |  |  |  | 400 |  |  | 0.95 | 568.632 | 409.944
VS02+06 | นิภาพร + ชุติมันต์ | 40 | 0.96 | 38.4 | 412.8 | 297.6 | 144 | 153.6 | 115.2 | 180 | 60 | 180 |  | 140 | 36 | 650 | 282 | 500 | 2.4479 | Underproduction |  | 15.8333 | Neutral | ปกติ | 16.7708 | Neutral | ปกติ | 16.4167 | ปกติ |  | 25-0643-3 T.7,8=60+180 | 62.4 |  | 25-0643-3 T.8,9=60+180 | 87.2 |  |  | รอจัดงาน | 474 |  |  | 0.9 | 387 | 267.84
VS08+11 | นวลจันทร์+สุพิศ/ 50 | 46 | 0.88 | 40.48 | 435.16 | 313.72 | 151.8 | 161.92 | 121.44 | 125 |  | 29 |  | 150 | -26.8 | 861 | 219.604 | 304 | -4.4219 | Underproduction |  | 18.9327 | Neutral | ปกติ | 15.8991 | Neutral | ปกติ | 15.6046 | ปกติ |  | 25-0651-1 T.5,7=5+9+15/จบ.job | -159.72 |  |  | -131.16 |  |  | รอตรวจ |  |  |  | 0.7 | 346.15 | 219.604